## Sheet1
Task | Start Date | End Date | Duration
Identify problem and propose solution | 2023-12-22 | 2023-12-29 | 7
Conduct research | 2023-12-30 | 2024-01-04 | 5
Finalize project design and obtain approval | 2024-01-05 | 2024-01-12 | 7
Develop computer vision algorithm for ball tracking | 2024-01-01 | 2024-01-20 | 19
Establish connection between Raspberry Pi and Arduino | 2024-02-07 | 2024-02-14 | 7
Implement LCD screen and keypad for game setup | 2024-03-13 | 2024-03-30 | 17
Implement linear actuator | 2024-02-14 | 2024-03-20 | 35
Integrate solenoid with relay for ball striking | 2024-02-16 | 2024-02-23 | 7
Develop remote input for solenoid control | 2024-02-23 | 2024-03-02 | 8
Develop remote input for linear actuator (paddle) control | 2024-03-16 | 2024-04-10 | 25
Develop autonomous solution for solenoid control | 2024-05-02 | 2024-05-10 | 8
Develop autonomous solution for linear actuator control | 2024-04-06 | 2024-04-22 | 16
Implement goal counter | 2024-04-06 | 2024-04-22 | 16
Integrate buzzers and LEDs | 2024-04-22 | 2024-04-25 | 3
Implement ball redeploy mechanism | 2024-05-01 | 2024-05-10 | 9
Finalize 3D parts design and initiate printing | 2024-04-25 | 2024-05-10 | 15
Implement second linear actuator (paddle) and solenoid | 2024-04-22 | 2024-05-10 | 18
Assemble all parts and complete project | 2024-04-22 | 2024-06-02 | 41